No	Ref	Subject	Action Required	Owner	Meeting Date	Date Due	Progress / Comment	Date / Completed	Status
1	CM/24/02/51	Ofsted – Learning from our external environment	An update would come to the Public Board in 6 months (September) in relation to providers’ experience following the roll out of the SAF.	Chris Dzikiti	07/02/24	27/11/24	The paper was due to be presented to the Board in September but was deferred for consideration at the November meeting. It will be considered at this meeting.
2	CM/07/24/21	Report from the Executive Team: / Chief Inspectors’ Insights	The Regulatory Governance Committee should review the response to commitments identified for the CQC at the Skills for Care Adult Social Care Workforce Strategy launch.	James Bullion	24/07/24	27/11/24	We did not need to present it to RGC, as we had picked up those through updates, including regulatory matters to the Board / Relevant updates were shared with the Board in the ‘Regulatory Matters’ section of the ET report.
3	CM/09/24/23	Strategic and Policy Approach Towards an Anti-Racist Approach in CQC	JF to clarify the Board’s role in implementing change.	Joyce Frederick	25/09/24	5/02/25	Further information will be provided at the February 2025 meeting
4	CM/09/24/23	Strategic and Policy Approach Towards an Anti-Racist Approach in CQC	JF to highlight positive examples of addressing racism in future Board discussion.	Joyce Frederick	25/09/24	5/02/25	Further information will be provided at the February 2025 meeting
5	CM/09/24/24	WRES & WDES Report and Action Plan	JJ and NR to conduct a detailed examination of policies and procedures, outlining actions necessary to bring about significant change in Equality, Diversity, and Inclusion.	Jackie Jackson	25/09/24	5/02/25	Further information will be provided at the February 2025 meeting
6	CM/09/24/24	WRES & WDES Report and Action Plan	Sean Cornall to incorporate the auditing of EDI processes into next year’s audit plan.	Sean Cornall	25/09/24	27/11/24	When we engage with GIAA about next year’s programme, it would be included.
7	CM/09/24/41	National maternity inspection end of programme report and supporting improvement resource	CD to evaluate in 12 months, whether this initiative has led to any positive outcomes.	Chris Day	25/09/24	24/09/25	Further information will be provided at the September 2025 meeting

Status key:
- Red – overdue
- Geen - on track
- Blue – Complete or propose to close